## Claude Can Do
SEEMA BUILD — What Claude Can Do
These tasks are 100% code — Claude can build them in full
Item | Task | What Claude Delivers | Est. Time | Status
ITEM 04
04 | Backend: Raw HTTP → FastAPI | Full FastAPI project with routers, Pydantic models, middleware, auth, CORS, logging, error handling, OpenAPI docs | 7-10 days | Ready
04a | Port all ~120 endpoints | Every endpoint converted to FastAPI route functions with request/response validation |  | Ready
04b | Integration tests | Test suite for critical workflows (scan, policy gen, breach reporting) |  | Ready
04c | Structured logging | JSON-format logging for production log aggregation |  | Ready
ITEM 07
07 | Frontend: HTML → Next.js | Full Next.js project with TypeScript, 22 page components, shared component library, Tailwind CSS | 10-14 days | Ready
07a | Component library | Cards, stat grids, tables, modals, toasts as reusable components |  | Ready
07b | State management | React Context or Zustand for app-wide state |  | Ready
07c | Proper routing | URL-based routing replacing view toggling |  | Ready
07d | Responsive design | Tablet-friendly layout for iPad use |  | Ready
ITEM 02
02 | Multi-Tenancy Code | firm_id column on all 42 tables, firms table, row-level filtering on every query, provisioning flow | 4-6 days | Ready
02a | Data isolation testing | Test scripts proving Firm A cannot see Firm B's data |  | Ready
ITEM 03
03 | Authentication Code | bcrypt hashing, JWT with refresh tokens, rate limiting, RBAC (COLP/Partner/Solicitor/Admin/Staff) | 5-7 days | Ready
03a | Password reset flow | Full email-link reset with time-limited tokens |  | Ready
03b | Session management | Force logout, view active sessions, token revocation |  | Ready
ITEM 01
01 | Database Migration Scripts | SQLAlchemy models for all 42 tables, Alembic migration config, pgBouncer setup scripts | 3-5 days | Ready
01a | Migration tooling | Scripts to migrate data from SQLite → PostgreSQL |  | Ready
ITEM 05
05 | Regulatory Feed Scrapers | Python scrapers for SRA, ICO, Law Society, GOV.UK Content API | 10-14 days | Ready
05a | Claude API integration | Impact analysis prompts — affected areas, policies, urgency, actions per firm profile |  | Ready
05b | Background scheduler | Celery + Redis task config polling every 4-6 hours |  | Ready
ITEM 06
06 | Email Integration Code | SendGrid/SES integration, HTML templates (chaser, reminder, alert, digest), auto-chase logic | 5-7 days | Ready
06a | Delivery tracking | Sent/opened/bounced tracking, unsubscribe management |  | Ready
ITEM 08
08 | Infrastructure-as-Code | Dockerfiles, docker-compose, GitHub Actions CI/CD pipeline, Terraform scripts for AWS | 3-5 days | Ready
ITEM 11
11 | Billing Code (Stripe) | Stripe Billing integration, subscription management UI, feature gating, webhook handlers, dunning logic | 5-7 days | Ready
11a | VAT handling | UK-compliant automated invoicing with VAT |  | Ready
11b | Admin dashboard | Internal MRR, churn, trial conversion tracking |  | Ready
ITEM 12
12 | Onboarding Wizard | Multi-step flow: firm details → staff CSV upload → role assignment → email config → first scan | 5-7 days | Ready
12a | SRA register lookup | Auto-detect firm from SRA number, pre-fill details |  | Ready
12b | Default policy generation | Trigger policy generator for new firm on setup |  | Ready
ITEM 10
10a | DPIA document | Full Data Protection Impact Assessment for Seema | 2-3 days | Ready
10b | DPA template | Data Processing Agreement for client contracts |  | Ready
10c | Data retention policy | Documented retention and deletion policies |  | Ready
10d | Data export functionality | Code for firms to extract all their data |  | Ready

## You or Developer Must Do
SEEMA BUILD — What You / Developer Must Do
These require live accounts, credentials, third-party services, or physical actions
Item | Task | Why Claude Can't Do It | Who Does It | Estimated Cost
ACCOUNTS & CREDENTIALS
01 | Provision AWS RDS PostgreSQL | Requires your AWS account login, credit card, and IAM setup | You / Developer | ~£50-150/mo
03 | SSL certificate & domain setup | Requires purchasing seema.law domain and configuring DNS | You / Developer | ~£30-50/yr
06 | Create SendGrid/SES account | Requires your email, credit card, domain verification | You / Developer | Free-£15/mo
06a | Verify sending domain (DNS) | Add SPF/DKIM records to your domain registrar | You / Developer | Free
08 | Set up AWS account | Requires identity verification, credit card, billing setup | You / Developer | Pay-as-you-go
08a | Deploy to live servers | Requires SSH access, AWS console, environment variables | Developer | ~£100-300/mo
08b | Set up staging environment | Requires second server instance and database | Developer | ~£50-100/mo
11 | Create Stripe account | Requires your business details, bank account, ID verification | You | 2.9% + 20p/txn
THIRD-PARTY INTEGRATIONS
09 | Clio API developer account | Requires applying to Clio's partner programme and approval | You | Free to apply
09a | Test PMS sync with real data | Requires a live Clio account with real or test firm data | Developer | Clio subscription
09b | LEAP / PracticeEvolve APIs | Each PMS has its own partner programme and approval process | You | Varies
SECURITY & COMPLIANCE
10 | Cyber Essentials Plus cert | Requires assessment by certified body (IASME assessor) | You | £1,500-3,000
10a | Penetration test | Must be done by CREST-accredited firm on live system | Third party | £3,000-8,000
10b | SOC 2 Type I audit | Requires external auditor, 3-6 month process | Third party | £15,000-30,000
10c | ICO registration | Register as data controller with Information Commissioner | You | £40-2,900/yr
ONGOING OPERATIONS
05 | Monitor scraper health | SRA/ICO websites change structure — scrapers need maintenance | Developer | Ongoing
05a | Claude API costs | Pay for Claude API usage for regulatory analysis | You | ~£50-200/mo
08c | Database backup testing | Monthly restore tests on live backups | Developer | Ongoing
— | Customer support | Responding to firm queries, onboarding calls, training | You | Your time
— | Sales & outreach | Contacting firms, demos, closing deals, follow-ups | You | Your time

## Summary
SEEMA BUILD — Summary Split
Roadmap Item | Claude Can Do | You Must Do | Total Est. Days
01 — Database Migration | Migration scripts, SQLAlchemy models, Alembic config | Provision AWS RDS, set credentials | 3-5
02 — Multi-Tenancy | All code: firm_id columns, queries, provisioning, isolation tests | — | 4-6
03 — Auth & Security | All code: bcrypt, JWT, RBAC, rate limiting, sessions | SSL cert, domain purchase | 5-7
04 — Backend FastAPI | 100% — full rewrite of all 120 endpoints | — | 7-10
05 — Regulatory Feeds | All scrapers, Claude API integration, scheduler | Claude API account, ongoing monitoring | 10-14
06 — Email Integration | All code: templates, chase logic, tracking | SendGrid account, domain verification | 5-7
07 — Frontend Next.js | 100% — full rewrite of 22 views + component library | — | 10-14
08 — Hosting & Infra | Dockerfiles, CI/CD pipeline, Terraform | AWS account, deploy to servers | 3-5
09 — PMS Integration | OAuth flow code, sync logic (partial) | Clio partner account, live testing | 10-14
10 — Security Certs | DPIA, DPA, policies, data export code | Cyber Essentials, pen test, SOC 2 | Ongoing
11 — Billing (Stripe) | All code: integration, UI, gating, webhooks | Stripe account creation | 5-7
12 — Onboarding Flow | 100% — full wizard with SRA lookup | — | 5-7
BOTTOM LINE
Claude builds (code) | ~70-80% of total work | All application code, tests, infrastructure scripts
You handle (accounts) | ~15% of total work | AWS, Stripe, SendGrid, domain — sign up and hand over keys
Third parties (certs/audits) | ~5-10% of total work | Cyber Essentials, pen test, SOC 2 — only needed before Enterprise sales
Items 02, 04, 07, 12 are 100% Claude — zero dependency on anyone else