## Claude Builds
PHASE 1 — What Claude Builds (Code Your Developer Receives)
All of this is production-ready code. Claude writes it, your developer deploys it.
# | Deliverable | Exactly What You Get | Files Created | Order | Status
BACKEND — FastAPI Rewrite (Item 04)
1 | FastAPI project structure | Complete project scaffold: main.py, routers/, models/, services/, middleware/, config/. Replaces the 8,400-line demo-server.py with clean, modular code. | seema-api/ ├── main.py ├── config.py ├── routers/ (12 files) ├── models/ (10 files) ├── services/ (8 files) ├── middleware/ (4 files) | Build 1st | ☐ Pending
2 | All 120 endpoints ported | Every endpoint from demo-server.py converted to FastAPI route functions with Pydantic request/response models, proper error handling, and auto-generated API docs at /docs. | routers/dashboard.py routers/compliance.py routers/intake.py routers/staff.py routers/policies.py + 7 more router files | Build 1st | ☐ Pending
3 | Authentication middleware | bcrypt password hashing, JWT access tokens (15min) + refresh tokens, rate limiting (5 attempts/min on login), role-based access control for 5 roles: COLP, Partner, Solicitor, Admin, Staff. | middleware/auth.py middleware/rate_limit.py models/auth.py routers/auth.py | Build 1st | ☐ Pending
4 | Multi-tenancy layer | firm_id column on every table. Every database query filtered by firm_id automatically via SQLAlchemy middleware. Firm provisioning endpoint. Data isolation guaranteed. | middleware/tenant.py models/firm.py services/provisioning.py | Build 1st | ☐ Pending
DATABASE (Item 01 + 02)
5 | SQLAlchemy models for all 42 tables | Every table from demo-workflows.db defined as a SQLAlchemy ORM model with proper relationships, indexes, and constraints. All include firm_id for multi-tenancy. | models/compliance.py models/staff.py models/intake.py models/policies.py models/audit.py + 5 more | Build 1st | ☐ Pending
6 | Alembic migration system | Database migration framework. Initial migration creates all 42 tables in PostgreSQL. Future schema changes are versioned and reversible. | alembic.ini alembic/ ├── env.py ├── versions/ │ └── 001_initial.py | Build 1st | ☐ Pending
7 | SQLite → PostgreSQL migration script | One-shot script that reads all data from demo-workflows.db and inserts it into PostgreSQL. Handles type conversions and data validation. | scripts/migrate_sqlite_to_pg.py | Build 1st | ☐ Pending
FRONTEND — Next.js Rewrite (Item 07)
8 | Next.js project with TypeScript | Complete Next.js 14 project replacing the 290KB single HTML file. App Router, TypeScript, Tailwind CSS configured with Seema's navy theme. | seema-web/ ├── app/ ├── components/ ├── lib/ ├── styles/ ├── tailwind.config.ts ├── next.config.js | Build 2nd | ☐ Pending
9 | 22 page components | Each sidebar view becomes its own page: /dashboard, /staff, /intake, /deadlines, /alerts, /policies, /breaches, /supervision, /matters, etc. Proper URL routing. | app/dashboard/page.tsx app/staff/page.tsx app/intake/page.tsx app/deadlines/page.tsx + 18 more pages | Build 2nd | ☐ Pending
10 | Shared component library | Reusable UI components: StatCard, DataTable, Modal, Toast, StatusBadge, ComplianceScore, ActionButton, SearchBar, DatePicker, FileUpload. All styled with Tailwind. | components/ui/ ├── StatCard.tsx ├── DataTable.tsx ├── Modal.tsx ├── Toast.tsx ├── StatusBadge.tsx + 10 more | Build 2nd | ☐ Pending
11 | State management & API client | Zustand stores for auth, firm, notifications. API client with automatic JWT refresh, error handling, and loading states. | lib/stores/ lib/api-client.ts lib/hooks/ | Build 2nd | ☐ Pending
12 | Responsive tablet layout | Collapsible sidebar, responsive data tables, touch-friendly buttons. COLPs using iPads can access everything. | Built into all components | Build 2nd | ☐ Pending
REGULATORY FEEDS (Item 05)
13 | SRA scraper | Python scraper that polls sra.org.uk/sra/news for new enforcement actions, warning notices, guidance updates, and regulatory changes. Parses HTML, extracts structured data. | services/scrapers/sra_scraper.py | Build 3rd | ☐ Pending
14 | ICO + Law Society + GOV.UK scrapers | Same pattern for ICO enforcement actions, Law Society practice notes, and GOV.UK legislative updates via their Content API. | services/scrapers/ico_scraper.py services/scrapers/lawsoc_scraper.py services/scrapers/govuk_scraper.py | Build 3rd | ☐ Pending
15 | Claude AI impact analysis | When a new regulatory update is scraped, sends it to Claude API with the firm's profile to get: affected practice areas, policies needing update, urgency level, recommended actions, staff to notify. | services/ai_analysis.py services/prompts/regulatory_impact.py | Build 3rd | ☐ Pending
16 | Celery background scheduler | Celery worker + Redis broker. Polls regulatory sources every 4-6 hours. Processes updates asynchronously. Retry logic for failed scrapes. | celery_app.py tasks/regulatory_tasks.py tasks/email_tasks.py | Build 3rd | ☐ Pending
EMAIL (Item 06)
17 | SendGrid integration + templates | Full email service: training overdue chaser, file review reminder, breach alert, weekly compliance digest, welcome email. HTML templates branded with Seema design. | services/email_service.py templates/email/ ├── training_chaser.html ├── breach_alert.html ├── weekly_digest.html + 4 more | Build 3rd | ☐ Pending
18 | Auto-chase system | Background task that checks daily for: overdue training → sends chaser, CDD expiring → sends reminder, file review due → sends nudge. Escalation after 3 ignored chasers. | tasks/chase_tasks.py services/chase_engine.py | Build 3rd | ☐ Pending
INFRASTRUCTURE (Item 08)
19 | Docker setup | Dockerfiles for API and frontend. docker-compose.yml that spins up: FastAPI + Nginx + PostgreSQL + Redis + Celery worker. One command to run everything. | Dockerfile.api Dockerfile.web docker-compose.yml nginx/nginx.conf | Build 1st | ☐ Pending
20 | CI/CD pipeline | GitHub Actions workflow: push to main → run tests → build Docker images → deploy to your VPS via SSH. Automatic deployments. | .github/workflows/deploy.yml .github/workflows/test.yml | Build 1st | ☐ Pending
21 | Nginx config for seemaai.co.uk | Reverse proxy config: HTTPS with Let's Encrypt auto-renewal, API at api.seemaai.co.uk, frontend at seemaai.co.uk. Security headers, gzip, rate limiting. | nginx/seemaai.conf scripts/setup-ssl.sh | Build 1st | ☐ Pending
BILLING (Item 11)
22 | Stripe integration | Full Stripe Billing: create customer, subscribe to plan, upgrade/downgrade, cancel. Webhook handler for payment events. Feature gating based on subscription tier. | services/billing.py routers/billing.py models/subscription.py | Build 3rd | ☐ Pending
23 | Subscription management UI | Settings page where firm admin can view plan, upgrade, download invoices, update payment method. Internal admin dashboard showing MRR, churn, trial conversions. | app/settings/billing/page.tsx app/admin/revenue/page.tsx | Build 3rd | ☐ Pending
ONBOARDING (Item 12)
24 | Onboarding wizard | Multi-step flow: Enter SRA number → auto-fill firm details from SRA register → upload staff CSV → assign COLP/COFA/MLRO roles → configure email preferences → run first compliance scan → go live. | app/onboarding/page.tsx routers/onboarding.py services/sra_lookup.py | Build 3rd | ☐ Pending
LEGAL DOCUMENTS
25 | Data Protection Impact Assessment | Full DPIA covering: what personal data Seema processes, legal basis, risks assessment, security controls, data flows, retention periods. ICO-compliant format. | Seema-DPIA.docx | Anytime | ☐ Pending
26 | Data Processing Agreement template | DPA for client contracts covering: data types processed, processing purposes, security measures, sub-processors (AWS, SendGrid, Stripe, Anthropic), breach notification (72hrs), deletion on termination. | Seema-DPA-Template.docx | Anytime | ☐ Pending
27 | Privacy Policy + Cookie Policy | UK GDPR-compliant privacy policy for seemaai.co.uk. Cookie policy covering analytics and session cookies with consent mechanism. | Seema-Privacy-Policy.md Seema-Cookie-Policy.md | Anytime | ☐ Pending
28 | Breach notification procedure | Step-by-step internal procedure: detect → contain → assess severity → notify ICO within 72hrs → notify affected firms → remediate → post-mortem. | Seema-Breach-Procedure.docx | Anytime | ☐ Pending
29 | Record of Processing Activities | ROPA register listing every processing activity, data categories, legal basis, recipients, transfers, retention periods. UK GDPR Article 30 compliant. | Seema-ROPA.xlsx | Anytime | ☐ Pending
30 | Security page content | Full content for seemaai.co.uk/security — encryption standards, hosting location, backup policy, access controls, incident response, certifications, sub-processors. | security-page-content.md | Anytime | ☐ Pending
31 | Incident response plan | Full IRP: roles & responsibilities, severity classification, escalation paths, communication templates, recovery procedures, post-incident review process. | Seema-Incident-Response.docx | Anytime | ☐ Pending

## You Do (SARDAR)
PHASE 1 — What You (SARDAR) Must Do Personally
Nobody else can do these — they need your identity, bank details, or decisions
# | Task | Exactly What To Do (Step by Step) | Cost | When | Status
WEEK 1 — BUSINESS SETUP
1 | Register Ltd company | Go to gov.uk/set-up-limited-company. Register online (takes 20 mins). Name: 'Seema Compliance Ltd' or similar. You'll need: your name, address, SIC code 62012 (business/software development). You get a company number and certificate of incorporation. | £12-50 | Day 1 | ☐
2 | Open business bank account | Apply online with Starling, Tide, or Monzo Business. You'll need your Companies House number from step 1. Takes 1-3 days to verify. This is where Stripe payouts go. | Free | Day 2 | ☐
3 | Get professional indemnity insurance | Go to Hiscox, Simply Business, or PolicyBee. Get a tech PI policy covering software/SaaS. Cover level: £250K-500K is fine to start. Law firms WILL ask if you have this. Without it, some won't sign. | £300-800/yr | Day 3 | ☐
4 | Register with ICO | Go to ico.org.uk/registration. Register as a data controller. You process personal data of firm staff and their clients. Takes 10 minutes. This is a legal requirement — processing without registration is a criminal offence under the Data Protection Act 2018. | £40-60/yr | Day 3 | ☐
5 | Get an Anthropic API key | Go to console.anthropic.com. Sign up. Add payment method. Generate an API key. This powers Seema's AI regulatory analysis and knowledge engine. Give the API key to your developer. | Pay-as-you-go ~£50-200/mo | Day 3 | ☐
WEEK 2 — ACCOUNTS & SERVICES
6 | Create SendGrid account | Go to sendgrid.com. Sign up. Verify your email. Add seemaai.co.uk as a verified sender domain — this requires adding 3 DNS records (CNAME) to your domain registrar. SendGrid gives you the exact records to add. Free tier sends 100 emails/day. | Free | Day 5 | ☐
7 | Create Stripe account | Go to stripe.com. Sign up with your business details (Seema Compliance Ltd, Companies House number). Connect your business bank account. Verify your identity (passport/driving licence). This handles all firm billing and subscriptions. | 2.9% + 20p per transaction | Day 5 | ☐
8 | Set up GitHub repository | Go to github.com. Create a private repository called 'seema'. Invite your developer. This is where Claude's code goes and where CI/CD deploys from. If you already have one, skip this. | Free | Day 5 | ☐
9 | Point domain to VPS | Log into your domain registrar for seemaai.co.uk. Add an A record pointing to your VPS IP address. Add a second A record for api.seemaai.co.uk pointing to the same IP. DNS propagation takes up to 48 hours. | Free | Day 5 | ☐
WEEK 2-3 — LEGAL REVIEW
10 | Get Terms of Service reviewed | Claude writes the draft Terms of Service. You MUST get a solicitor to review it. You're selling to solicitors — they will read every clause. Budget £500-1,500 for a tech-savvy commercial solicitor. Ask them to check: liability caps, SLA commitments, termination terms, IP ownership, data ownership on exit. | £500-1,500 | Week 2-3 | ☐
11 | Get DPA reviewed | Claude writes the DPA template. Have the same solicitor review it. Key areas: sub-processor list accuracy, breach notification timing (72hrs), data deletion obligations on contract end, international transfer safeguards. | Included above | Week 2-3 | ☐
12 | Get Privacy Policy reviewed | Claude writes the draft. Solicitor checks it meets UK GDPR requirements. Quick review — most of the work is in the drafting. | Included above | Week 2-3 | ☐
WEEK 3-4 — DECISIONS ONLY YOU CAN MAKE
13 | Finalise pricing tiers | You have the pricing spreadsheet. Decide: Essentials £299 or higher? Professional £599 or higher? Annual discount 2 months free or different? Free trial 30 days or 14? Fined firm offer — 6 months or 3? These get built into Stripe and the feature gating. | Free | Week 3 | ☐
14 | Define feature gating per tier | Decide exactly which sidebar views each tier gets. Recommendation: Essentials = Dashboard + Deadlines + Reg Alerts + Breach Log + Audit Report + Staff Training. Professional = everything. Tell your developer. | Free | Week 3 | ☐
15 | Write your 'About' / company story | For the website. Who are you, why did you build Seema, what problem does it solve. Firms buy from people they trust — especially in legal. Your background and motivation matter. | Free | Week 3 | ☐
16 | Prepare pilot firm outreach | You have 8 fined firm analysis docs and email sequences ready. Customise each email with the firm's specific fine details. Prepare to send once the product is live. Don't send before it's ready. | Free | Week 4 | ☐
YOUR TOTAL PHASE 1 SPEND
Companies House registration |  |  | £12-50
Professional indemnity insurance |  |  | £300-800/yr
ICO registration |  |  | £40-60/yr
Solicitor review (ToS + DPA + Privacy) |  |  | £500-1,500
SendGrid / Stripe / GitHub |  |  | Free
Anthropic API (monthly) |  |  | ~£50-200/mo
VPS (already have) |  |  | Already paid
Domain (already have) |  |  | Already paid
TOTAL ONE-OFF TO LAUNCH |  |  | £850 - £2,400

## Developer Does
PHASE 1 — What Your Developer Does
Developer receives Claude's code and deploys it to your VPS. Their job is deployment, not building from scratch.
# | Task | What The Developer Does | Depends On | Status
WEEK 1-2 — VPS SETUP
1 | Install Docker on VPS | SSH into your VPS. Install Docker and Docker Compose. This is the foundation everything runs on. Takes 30 minutes. | VPS access | ☐
2 | Install PostgreSQL | Using docker-compose.yml from Claude's code. Set database password, create seema database, enable encryption at rest. Configure automated daily backups. | Docker installed | ☐
3 | Install Redis | Part of docker-compose.yml. Redis is the message broker for Celery (background tasks like regulatory feed scraping and email sending). | Docker installed | ☐
4 | Set up SSL with Let's Encrypt | Run Claude's setup-ssl.sh script. Installs Certbot, generates SSL certificate for seemaai.co.uk and api.seemaai.co.uk. Configures auto-renewal (certs expire every 90 days). | Domain pointed to VPS | ☐
5 | Deploy Nginx | Using Claude's nginx config. Reverse proxy: seemaai.co.uk → Next.js frontend, api.seemaai.co.uk → FastAPI backend. HTTPS enforced, security headers set. | SSL certificate | ☐
WEEK 2-3 — DEPLOY APPLICATION
6 | Clone GitHub repo to VPS | Pull Claude's code from your GitHub repository. Set environment variables: database URL, Stripe keys, SendGrid API key, Anthropic API key, JWT secret. | GitHub repo + all API keys from SARDAR | ☐
7 | Run database migrations | Run 'alembic upgrade head' to create all 42 tables in PostgreSQL. Run migration script to import demo data if needed for testing. | PostgreSQL running | ☐
8 | Build and start Docker containers | Run 'docker-compose up -d'. This starts: FastAPI API, Next.js frontend, Celery worker, Nginx. Verify all services are running. | All env variables set | ☐
9 | Verify SendGrid domain | SARDAR adds the DNS records. Developer verifies they propagated correctly and sends a test email to confirm delivery. | SARDAR added DNS records | ☐
10 | Configure Stripe webhooks | In Stripe dashboard, set webhook URL to api.seemaai.co.uk/webhooks/stripe. Add the webhook signing secret to environment variables. | Stripe account created by SARDAR | ☐
WEEK 3-4 — TESTING & HARDENING
11 | Run integration tests | Execute Claude's test suite against the live deployment. Fix any environment-specific issues (file permissions, network, DNS). | App deployed | ☐
12 | Set up monitoring | Install Sentry for error tracking (free tier). Set up Better Uptime or UptimeRobot to monitor seemaai.co.uk (free tier). Configure alerts to your email/Slack. | App deployed | ☐
13 | Run OWASP ZAP vulnerability scan | Download OWASP ZAP (free). Run automated scan against seemaai.co.uk. Fix any critical or high severity findings. Save the report. | App deployed | ☐
14 | Test backup and restore | Trigger a database backup. Delete a test record. Restore from backup. Verify the record is back. This proves your backup system works before real firm data is in there. | Backups configured | ☐
15 | Set up CI/CD | Configure GitHub Actions using Claude's deploy.yml. Test by pushing a small change and verifying it auto-deploys to the VPS. | GitHub repo + SSH keys | ☐
16 | Final smoke test | Register a test firm through the onboarding wizard. Add staff. Run a compliance scan. Generate a PDF report. Send a test chaser email. If all works, you're ready to go live. | Everything above | ☐

## Timeline
PHASE 1 — 4-Week Timeline (All 3 Streams in Parallel)
Week | Claude Builds | SARDAR Does | Developer Does
Week 1 | FastAPI project structure All 120 endpoints ported Auth middleware Multi-tenancy layer SQLAlchemy models Alembic migrations Docker setup Nginx config | Register Ltd company Open bank account Get PI insurance Register with ICO Get Anthropic API key | Install Docker on VPS Install PostgreSQL Install Redis
Week 2 | Next.js project setup 22 page components Component library State management API client | Create SendGrid account Create Stripe account Set up GitHub repo Point domain to VPS Send legal docs for solicitor review | Set up SSL Deploy Nginx Clone repo Run migrations Deploy first build
Week 3 | Regulatory feed scrapers Claude AI analysis integration Celery scheduler Email templates Auto-chase system | Finalise pricing decisions Define feature gating Write company story Review solicitor feedback | Verify SendGrid domain Configure Stripe webhooks Run integration tests Set up monitoring
Week 4 | Stripe billing integration Subscription management UI Onboarding wizard All legal documents Security page content | Approve final legal docs Prepare pilot firm emails Prepare demo script | OWASP vulnerability scan Test backup & restore Set up CI/CD Final smoke test GO LIVE
END OF WEEK 4: Seema is live at seemaai.co.uk — send outreach emails to fined firms