## Pre-Launch Essentials
SEEMA — Security & Legal Roadmap to First Sale
Everything you must complete before a law firm can legally and safely use Seema
# | Task | What It Is & Why You Need It | Who | Cost | When | Status
PHASE 1 — MUST HAVE BEFORE FIRST CUSTOMER (Weeks 1-4)
LEGAL — BUSINESS FORMATION
1 | Register a limited company | You need a legal entity to enter contracts. Register with Companies House as a Ltd company. Seema Compliance Ltd or similar. | You | £12-50 | Week 1 | ☐ Not Started
2 | Business bank account | Separate account for Seema revenue. Needed for Stripe payouts and expense tracking. | You | Free-£10/mo | Week 1 | ☐ Not Started
3 | Professional indemnity insurance | Firms will ask if you carry PI insurance. If your software causes a compliance failure and they get fined, this protects you. Non-negotiable for selling to law firms. | You | £300-800/yr | Week 1 | ☐ Not Started
4 | Register with ICO as data controller | You are processing personal data of law firm staff and their clients. UK GDPR requires you to register with the Information Commissioner's Office. Failure to register is a criminal offence. | You | £40-60/yr | Week 1 | ☐ Not Started
LEGAL — CONTRACTS & POLICIES
5 | Terms of Service | Your contract with firms. Covers licensing, liability limits, acceptable use, termination, data ownership. Must be reviewed by a solicitor — you're selling to solicitors, they will read every word. | You + Solicitor | £500-1,500 | Week 2 | ☐ Not Started
6 | Privacy Policy | Required by UK GDPR. Explains what personal data you collect, why, how long you keep it, and data subject rights. Must be published on your website. | You + Solicitor | £300-800 | Week 2 | ☐ Not Started
7 | Data Processing Agreement (DPA) | Required by UK GDPR Article 28 when you process data on behalf of a firm (you're the processor, they're the controller). Must cover: data types, processing purposes, security measures, sub-processors, breach notification timelines. | Claude + Solicitor review | £200-500 | Week 2 | ☐ Not Started
8 | Cookie policy | If your web app uses any cookies or analytics, UK PECR regulations require explicit consent and a published policy. | Claude | Free | Week 2 | ☐ Not Started
9 | Acceptable Use Policy | What users can and can't do on your platform. Protects you if a firm misuses the system. | Claude | Free | Week 2 | ☐ Not Started
DATA PROTECTION — LEGAL REQUIREMENTS
10 | Data Protection Impact Assessment (DPIA) | Required by UK GDPR Article 35 because you're processing sensitive legal/compliance data at scale. Documents the risks and your mitigations. The ICO can request this at any time. | Claude | Free | Week 2 | ☐ Not Started
11 | Record of Processing Activities (ROPA) | Required by UK GDPR Article 30. A register of all personal data processing activities — what data, why, where stored, who has access, retention periods. | Claude | Free | Week 2 | ☐ Not Started
12 | Data breach notification procedure | UK GDPR requires you to notify the ICO within 72 hours of a personal data breach, and notify affected individuals without undue delay. You need a documented procedure before it happens. | Claude | Free | Week 2 | ☐ Not Started
13 | Subject access request (SAR) procedure | Data subjects (firm staff, their clients) can request all data you hold on them. You have 30 days to respond. Need a process and the technical ability to extract it. | Claude + Developer | Free | Week 2 | ☐ Not Started
TECHNICAL SECURITY — MINIMUM VIABLE
14 | HTTPS everywhere (TLS 1.2+) | All data in transit must be encrypted. No exceptions. Use Let's Encrypt for free SSL or AWS Certificate Manager. | Developer | Free | Week 3 | ☐ Not Started
15 | Encryption at rest (AES-256) | All data stored in your database must be encrypted. AWS RDS supports this natively — just enable it. | Developer | Free | Week 3 | ☐ Not Started
16 | Secure authentication | bcrypt password hashing, JWT tokens with short expiry, rate limiting on login. Already in the roadmap. | Claude/Developer | Free | Week 3 | ☐ Not Started
17 | Role-based access control | COLP sees everything, staff see only their tasks. A junior solicitor must not access another firm's data or admin settings. | Claude/Developer | Free | Week 3 | ☐ Not Started
18 | Automated backups | Daily database backups with 30-day retention. Test a restore before going live. If you lose a firm's compliance data, your reputation is finished. | Developer | ~£20/mo | Week 3 | ☐ Not Started
19 | Audit logging | Log every significant action: who logged in, who viewed what, who changed what, when. Firms will ask for this — they need it for their own SRA compliance. | Claude/Developer | Free | Week 3 | ☐ Not Started
20 | Vulnerability scanning | Run OWASP ZAP or similar against your live site before launch. Fix any critical or high findings. Free tools exist. | Developer | Free | Week 4 | ☐ Not Started
21 | Secure hosting (UK region) | AWS eu-west-2 (London) or Azure UK South. Law firms need UK data residency. This is the first question a managing partner's IT person will ask. | Developer | ~£100-300/mo | Week 3 | ☐ Not Started
PHASE 2 — SHOULD HAVE WITHIN 3 MONTHS (Firms 1-10)
TRUST SIGNALS
22 | Cyber Essentials certification | UK government-backed security standard. The SRA recommends it. Shows firms you take security seriously. Basic version is self-assessed; Plus requires external audit. | You + Assessor | £300 (Basic) £1,500 (Plus) | Month 2-3 | ☐ Not Started
23 | Published security page on website | A page at seema.law/security listing your security measures: encryption, hosting location, backup policy, access controls, certifications. Firms want to see this before buying. | Claude | Free | Month 2 | ☐ Not Started
24 | Uptime monitoring & status page | Use Better Uptime or similar to monitor your site. Publish a status page. If Seema goes down during a firm's SRA audit, they need to know when it's coming back. | Developer | Free-£20/mo | Month 2 | ☐ Not Started
OPERATIONAL SECURITY
25 | Incident response plan | Documented procedure for: security breach detected → contain → investigate → notify affected firms → notify ICO (if required) → remediate → post-mortem. Write it before you need it. | Claude | Free | Month 2 | ☐ Not Started
26 | Sub-processor register | UK GDPR requires you to list all third parties who process data on your behalf: AWS (hosting), SendGrid (email), Stripe (billing), Anthropic (AI analysis). Firms must be able to see this list. | Claude | Free | Month 2 | ☐ Not Started
27 | Staff security training | If you hire anyone, they need security awareness training. Even if it's just you, document that the founder has completed security training. Firms will ask. | You | Free (online) | Month 3 | ☐ Not Started
28 | Penetration test (basic) | A basic pen test from a UK firm. Doesn't need to be CREST-accredited at this stage. Shows firms you've been independently tested. Save the report — firms will want to see it. | Third party | £1,500-3,000 | Month 3 | ☐ Not Started
PHASE 3 — NICE TO HAVE FOR GROWTH (Firms 10-50)
SCALE TRUST
29 | Cyber Essentials Plus (if not done) | The externally assessed version. Stronger signal. Required by some government-adjacent organisations. Worth doing once revenue justifies it. | You + Assessor | £1,500-3,000 | Month 6 | ☐ Not Started
30 | ISO 27001 preparation | The gold standard for information security management. Don't certify yet — it costs £10K+ and takes 6-12 months. But start building towards it: document your ISMS, risk register, controls. | You + Consultant | £2,000-5,000 prep | Month 6-12 | ☐ Not Started
31 | CREST penetration test | A pen test from a CREST-accredited firm carries more weight with larger firms. Do this when you're targeting firms with 20+ solicitors. | Third party | £3,000-8,000 | Month 6-12 | ☐ Not Started
32 | Formal SLA (uptime guarantee) | Once you have enough operational history, publish a Service Level Agreement with uptime commitments (99.5% or 99.9%) and credit policies for downtime. | You + Solicitor | £500-1,000 | Month 6 | ☐ Not Started
33 | SOC 2 Type I | Only if you're targeting Top 100 firms or corporate legal departments. Most small/mid firms don't know what it is and won't ask. Skip until revenue exceeds £500K/yr. | Third party | £15,000-30,000 | Year 2+ | ☐ Not Started
COST SUMMARY
Phase 1 — Before first customer (must-spend) |  |  | £1,350 - £3,700 |  | ICO reg + insurance + legal docs + hosting
Phase 2 — Within 3 months (recommended) |  |  | £1,800 - £5,000 |  | Cyber Essentials + basic pen test
Phase 3 — Growth stage (optional, revenue-funded) |  |  | £5,000 - £30,000+ |  | ISO 27001 prep, CREST pen test, SOC 2 (skip if not needed)
To legally sell to your first firm you need ~£1,500 and 4 weeks. Everything else scales with revenue.